## Project Completion
Truck | Not Completed | Completed | Total Items | Completed %
1st | 0 | 18 | 18 | 100%
2nd | 0 | 3 | 3 | 100%
3rd | 0 | 3 | 3 | 100% | Not Completed | Completed
Total | 0 | 24 | 24 | 100% | 0 | 24

## Resource Management
Resource Management | Budget Hours | 280 | Date: | 2025-05-15 | Expected Working Days: | 45 | Working Days Utilized | 32 | Working Days Saved | 13 | Holiday Days | 2
Date | Collective Hours | People | Worked | Description | Hours Worked Already | 229.5 | Hours Remaining | 50.5 | Hours Saved | 50.5 | Team Members Utilized
2023-05-23 | 6 | 1 | YES |  |  | 81.96% | [6 empty] | 2023-05-23 | 6
2023-05-24 | 8 | 2 | YES |  | Ahead of Schedule | 18.04% | [6 empty] | 2023-05-24 | 14
2023-05-25 | 6 | 1 | YES | [9 empty] | 2023-05-25 | 20
2023-05-26 | 5.5 | 1 | YES |  |  |  | Project | [5 empty] | 2023-05-26 | 25.5
2023-05-29 | 7 | 1 | YES | Team Member Out | [8 empty] | 2023-05-29 | 32.5
2023-05-30 | 6 | 1 | YES |  |  |  | Material | [5 empty] | 2023-05-30 | 38.5
2023-05-31 | 8 | 3 | YES |  |  |  | 3000 | [5 empty] | 2023-05-31 | 46.5
2023-06-01 | 10 | 1 | YES |  |  |  | Amount per Hour | Time |  |  |  |  | 2023-06-01 | 56.5
2023-06-02 | 9 | 2 | YES |  |  |  | 48 | [5 empty] | 2023-06-02 | 65.5
2023-06-05 | 2 | 1 | YES | Team Member Out |  | Actual | 11016 | [5 empty] | 2023-06-05 | 67.5
2023-06-06 | 6 | 2 | YES | Team Member Out |  | Expected | 16440 | [5 empty] | 2023-06-06 | 73.5
2023-06-07 | 11 | 2 | YES | Team Member Out |  |  | Difference | [5 empty] | 2023-06-07 | 84.5
2023-06-08 | 9 | 2 | YES | Team Member Out |  |  | 5424 | [5 empty] | 2023-06-08 | 93.5
2023-06-09 | 9 | 2 | YES | Team Member Out |  |  | 32.99% | [5 empty] | 2023-06-09 | 102.5
2023-06-12 | 12 | 2 | YES | [9 empty] | 2023-06-12 | 114.5
2023-06-13 | 17 | 2 | YES | [9 empty] | 2023-06-13 | 131.5
2023-06-14 | 13.5 | 2 | YES | [9 empty] | 2023-06-14 | 145
2023-06-15 | 20 | 3 | YES | [9 empty] | 2023-06-15 | 165
2023-06-16 | 11.5 | 2 | YES | [9 empty] | 2023-06-16 | 176.5
2023-06-19 | 4.5 | 1 | YES | [9 empty] | 2023-06-19 | 181
2023-06-20 | 10 | 1 | YES | [9 empty] | 2023-06-20 | 191
2023-06-21 | 8 | 1 | YES | [9 empty] | 2023-06-21 | 199
2023-06-22 | 6 | 1 | YES | [9 empty] | 2023-06-22 | 205
2023-06-23 | 7 | 2 | YES | [9 empty] | 2023-06-23 | 212
2023-06-26 | 0 | 0 | YES | [9 empty] | 2023-06-26 | 212
2023-06-27 | 5 | 1 | YES | [9 empty] | 2023-06-27 | 217
2023-06-28 | 3 | 1 | YES | [9 empty] | 2023-06-28 | 220
2023-06-29 | 0 | 0 | NO | [9 empty] | 2023-06-29 | 220
2023-06-30 | 3 | 1 | YES | [9 empty] | 2023-06-30 | 223
2023-07-03 | 1 | 1 | YES | [9 empty] | 2023-07-03 | 224
2023-07-04 | 0 | 0 | NO | [9 empty] | 2023-07-04 | 224
2023-07-05 | 0 | 0 | YES | [9 empty] | 2023-07-05 | 224
2023-07-06 | 2.5 | 1 | YES | [9 empty] | 2023-07-06 | 226.5
2023-07-07 | 0 | 0 | NO | [9 empty] | 2023-07-07 | 226.5
2023-07-10 | 3 | 1 | YES | [9 empty] | 2023-07-10
2023-07-11 | [12 empty] | 2023-07-11
2023-07-12 | [12 empty] | 2023-07-12
2023-07-13 | [12 empty] | 2023-07-13
2023-07-14 | [12 empty] | 2023-07-14
2023-07-17 | [12 empty] | 2023-07-17
2023-07-18 | [12 empty] | 2023-07-18
2023-07-19 | [12 empty] | 2023-07-19
2023-07-20 | [12 empty] | 2023-07-20
2023-07-21 | [12 empty] | 2023-07-21
2023-07-24 | [12 empty] | 2023-07-24
TOTAL | 229.5 | 8 | 32